## Sheet1
Risk Register for Hotel Booking System
Prepared by: |  | PhuongNTL |  |  | Date: | 14/09/2016
No | Rank | Risk | Description | Category | Root Cause | Triggers | Avoidance plan | Contingency plan | Fallback plan | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 1 | Lack of team members |  | People | Member leaves team | Dissatisfied with project or other members | Team leader need to have a meeting with this member and suggest him still be there. | Resolve the problems. For example: talk some sense into him | Continue with remaining member |  | PhuongNTL | low | high
2 | 3 | Conflict among team members |  | People | Team member doesn't understand each others | Has issue inside team | Plan some team buildings to improve teammate | Have a meeting to resolve conflict problem | Switch member to other team. |  | PhuongNTL | medium | high
3 | 4 | Requirement is changed after project is started |  | Process | SRS not good (not realistic, not feasibility, not meet customer needs) | Customer (user) make change request. Or project team cannot develop the system as desciption in SRS. | Requirement should be paid a lot of attention. SRS should be reviewd carefully by PM and the supervisor. | With each requirement changes, the project tema should have a meeting to analysis the change requests and take actions. | Re-estimate and update plan. |  | PhuongNTL | high | medium
4 | 5 | Team member do not meet the deadline |  | Process | Undisciplined and habit of team member, loose management | Have a deadline | Setting rule and minus of do not meet the deadline: lost money and named at meeting minute. | Punish the member do not meet the deadline. Working over time. | Ask for help from out of team, supervisors. |  | PhuongNTL | medium | medium
5 | 7 | Inability to verify/validate products against requirements. |  | Process |  | Inability to verify/validate products against requirements. | Print out the result to check by normal eyes. Debug into code to see how the code is running | Print out the result to check by normal eyes. Debug into code to see how the code is running | Ask for help from supervisors |  | PhuongNTL | medium | low
6 | 10 | Delivery project doesn’t meet requirement |  | Process | Team member not understand requirement | Can't delivery project | Teamlead have to review sourcecode and follow requirement | Fix in next version | Extend dealine |  | PhuongNTL | medium | low
7 |  | Difficulties when using new technologies |  |  | Team does not understand about new technologies such as: bootstrap, Jquery | The coding of schedule is slowed | The leader will trainning for team member | Take the time to learn new technologies | Ask for help from supervisors |  | CuongHD | medium | medium
8 |  | Developer experiencing difficulties in coding business | [8 empty] | CuongHD
9 |  | SQL Server is disabled |  |  | Account's azure is expired | SQL server is disabled |  |  |  |  | CuongHD
10 |  | Data in database is lost |  |  | Database system is changed when developing process | Waste of the time to add data to Database for testing process | Before changing the SQL system, backup SQL system | Often backup data in Database |  |  | CuongHD | medium | medium
11 |  | Source code is conflicted |  |  | Source code is changed or lost | Waste of the time to coding | Backup source code every day. |  |  |  | CuongHD | high | high